## Sheet1
| 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-02 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11
Deadlines | 2023-02-27: TMA01 - 28th February; 2023-05-01: TMA02 - 25th April; 2023-07-02: TMA03 - 4th July; 2023-09-11: EMA - 11th September
Write up | 2023-02-27: Finish writing up TMA01; 2023-04-24: Research LSEPI & EDI issues for TMA02 and begin write up; 2023-05-01: Finish writing up TMA02; 2023-06-26: TMA03 write up; 2023-08-14: EMA write up
Requirements, Evaluation, Feedback & Prototyping | 2023-03-06: Write requirements and user stories; 2023-03-20: Evaluate DB; 2023-04-03: Evaluate Map; 2023-04-10: Create prototype; 2023-04-17: Elicit user feedback and evaluate; 2023-05-22: Create prototype; 2023-05-29: Elicit user feedback and evaluate; 2023-07-31: Any final prototyping if necessary; 2023-08-07: Final evaluation & iteration
Database | 2023-03-13: Setup DB; 2023-05-15: Input full services/bathroom data
Map | 2023-03-27: Implement map
Search function | 2023-05-08: Program API calls, tags and map display
Contact | 2023-06-05: Implement messaging plugins
Privacy | 2023-06-12: Research privacy options; 2023-06-19: Implement closet mode
Calendar | 2023-07-10: Research calendar options; 2023-07-17: Implement calendar
User Interface | 2023-07-24: Improve appearance of UI
| 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-02
Deadlines | 2023-07-02: TMA03 - 4th July
Write up | 2023-06-26: TMA03 write up
Requirements, Evaluation, Feedback & Prototyping | 2023-06-05: Evaluate and create prototype; 2023-06-12: Elicit feedback on prototype; 2023-06-19: Evaluate prototype feedback
Database | 2023-05-08: Setup DB
Map | 2023-05-22: Implement Map
Search function | 2023-05-29: Program API calls, tags and map display
Contact
Privacy
Calendar
User Interface
| 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11
Deadlines | 2023-09-11: EMA - 11th September
Write up | 2023-08-21: EMA write up
Requirements, Evaluation, Feedback & Prototyping | 2023-08-07: Any final evaluation & prototyping if necessary
Database
Map
Search function | 2023-07-10: Implement search function to retrieve services based on user queries
Contact | 2023-07-17: implement plugins for contact info: phone, email, sms
Privacy | 2023-07-17: Implement 'closet mode' which conceals nature of the app on phone by changing name & icon
Calendar | 2023-07-24: Create the events calendar, which pulls existing events from facebook groups or a discord server
User Interface